**February, 2015 Accomplishments:**

* Permanent Fence Completed and Main Gate is Installed
* Continue installation / Repair of Geo Fabric and Finish Rock on Roads/Power Block
* Completed Grout for Electrical Buildings, and Misc Site Supports
* Completed Torqueing of CTG to Generator Coupling Bolts
* Completed Fit and Welding of Exhaust Diffuser to Duct Transition Cone
* Completed Modification of Turbine Exhaust Duct Elevation (Chipped Concrete)
* Completed Installation of Inlet Filter Media
* Continue Cleaning & Inspection of Inlet Filter & Evap Cooler Modules
* Continue Working Toward Completing All CTG Piping Installation
* Completed Installation and Modification of Fire Pump House Piping (Except Drain)
* Continue Installation of CO2 Fire Protection Piping
* Completed Inadvertent Ground Identification and Repairs in Field & IO Cabinets
* Continue PDC, CTG and Filter Building Terminations
* Completed Extra Cable Pulls and Terminations for Transformers, GCB & Switchyard Interface
* Completed Switchyard Relay Modified Setting Installation and Relay Testing
* Completed OMPA Switchyard to OG&E Substation Trip Checks
* Completed Functional Checks of 345 kV Breaker and Disconnect Switche
* Continue Final Installation of Plumbing, Electrical & HVAC In Service Building
* Completed Installation of Windows and Doors In Mechanical & Service Building
* Completed CTG Lube Oil Flush
* Completed Functional Testing of 4,160v Breakers and Relays
* Completed Functional Testing 480 v Switchgear Breakers and Relays
* Completed Testing Siemens Generator Protection Cabinet and Relays
* Begin Preliminary SFC and Exciter Checks / Commissioning
* Completed Initial Start and Run of Plant Air Compressor and Begin Instrument Air Line Cleaning Blows
* Completed Functional Testing of UAT & GSU Transformer Devices to Relay Cabinets
* ABB Completed Repairs and Replaced Damaged Fan and Leaking Valve on GSU

12 Turnover Packages, Of 32 Total (37.55%) Accepted By Start Up As Of 02/28/15.

**Overall Construction Progress: 92 % Complete**

**March, 2015 Look Ahead:**

* Continue Installation of Site Finish Rock and Grading
* Complete Service Building Interior Construction and Installation
* Complete Mechanical Building Equipment Connections
* Complete Generator Instrument & Accessory Installation
* Complete Turbine Insulation Installation
* Complete Combustion Turbine Piping Installations
* Complete Electrical Terminations & Instrumentation Installations
* Complete Turbine Hydraulic/Control Oil Flush
* Complete B.O.P. and CTG Electrical Terminations & Instrumentation
* Complete BOP and CTG DCS IO Checks
* Complete Functional / Trip Testing of Switchyard, Transformers, Circuit Breakers and Switchgear For Backfeed and First Fire
* Complete 345 kV Main Backfeed From OG&E
* Complete CTG System Component Start Up Activities
* Complete CTG Turning Gear Operation
* Complete CTG Commissioning to Support First Fire and Synchronization