**September, 2014 Accomplishments:**  
– Continuing Turbine and Generator Alignment  
– Continuing Installation of Fire Hydrants and Area Lighting  
– Continuing Storm Sewer Inlets and Piping  
– Continuing Installation of Finished Road Base  
– Continuing Assembly of Exhaust Stack  
– Completed Service Building Foundation  
– Set Fuel Gas Odorant Additive Skid  
– Started Service Building Structural Steel  
– Switch Yard Completed Except Jumpers to OG&E Lines  
– 345kV OG&E Substation Foundations 80% Complete

**Overall Construction Progress: 52.5%**